## Sheet2
SDLC Process and artefacts description | Mandatory requirement | Applicable to Project |  | Follow up |  | Comment | Deviation accepted
SDLC – 00- Pre-project Planning
The pre-project report with the following information: Initial Requirement(s), Project Scope, Overall Estimates and Go/No Go | No | Yes | 1 | Yes | 1
SDLC-10 Iteration 0 / Planning
SDLC 10-1 Project Initiation
Product Backlog with Id and Requirements columns | Yes | Yes | 1 | Yes | 1
Overall Architecture Diagram | Yes | Yes | 1 | Yes | 1
Project Standard Adherence Checklist (PSAC) | Yes | Yes | 1 | Yes | 1
Project Plan Information Sheet | Yes | Yes | 1 | Yes | 1
Project Plan (optional) | No | No | 0 | No | 0
SDLC 10-2 Prioritization of “Product Backlog”
Product Backlog with Id, Requirements and Priority | Yes | Yes | 1 | Yes | 1
SDLC 10-3 Sprint Planning Meeting
Overall Architecture Diagram | Yes | Yes | 1 | Yes | 1
The release plan in the PPIS | Yes | Yes | 1 | Yes | 1
Product Backlog with fields Id, Requirements, Priority, Besty Estimate and Worst Estimate | Yes | Yes | 1 | Yes | 1
Functional Specifications when required (optional) | No | No | 0 | No | 0
SDLC 20 Construction Iteration #1
SDLC 20-1 Scrum Meetings |  | Yes
Updated Product Backlog with time record | Yes | Yes | 1 | Yes | 1
Updated Scrum Meeting Notes | Yes | Yes | 1 | Yes | 1
SDLC 20-2 Construction Sprint
UML Sequence Diagram and UML Class Diagram as required (optional) | Yes | No | 0 | No | 0
Test results (showing traceability to the Product Backlog) | Yes | Yes | 1 | Yes | 1
Code in revision source control | Yes | Yes | 1 | Yes | 1
Design Document | No | No | 0 | No | 0
User and Operators Guides | No | Yes | 1 | No | 0
SDLC 20-3 Sprint Review
Updated Product Backlog | Yes | Yes | 1 | Yes | 1
Updated PPIS | Yes | Yes | 1 | No | 0
Change Request Status | No | Yes | 1 | No | 0
Updated Project Standard Adherence Checklist | Yes |  | 0 |  | 0
SDLC 30 – Release Iteration #1 (Should be repeated for each iteration)
Production Release | Yes | Yes | 1 | Yes | 1
Defect status report | Yes | Yes | 1 | No | 0
Final user and system documentation as required | Yes | Yes | 1 | No | 0
Training Material | No | Yes | 1 | No | 0
SDLC 40 – Production Iteration #1 (Should be repeated for each iteration)
Report of Requests for enhancement(s)if any | Yes | No | 0 | No | 0
Defect reports if any | Yes | Yes | 1 | Yes | 1
SDLC 50 – Retirement Iteration #1 (Should be repeated for each iteration)
Retirement status if any | Yes | No | 0 | No | 0
SDLC Standard Adherence | 72.73% | 22 |  | 16